## UI
NO | Issue Description | Status | Owner | Start Date | End Date | Comments | Testing
1 | When files are > 15, webserver is not responding | In Progress | Chakrapani | 1st Mar |  | Batch wise | Pass
2 | Not able to upload .jpeg | Fixed | Chakrapani | 28th Feb |  |  | Pass | Pass
3 | Delete the .p file when images are changed | In Progress | Jadeja | 1st Mar |  |  |  | failed
4 | Number of photos retrieved in the result section is limited 10, make it editable from GUI | Fixed | Jadeja | 1st Mar |  |  | Pass | failed
5 | The view/direction of photos displayed are not uniform | In Progress | Jadeja | 1st Mar |  |  |  | failed
6 | Images uploaded by photographer should be compressed and stored | OnHold | Chakrapani
7 | Move the server to the professional account | OnHold | Jadeja
8 | DAR on AWS, Google and Microsoft subscription | OnHold | Jadeja
9 | Download all button | In Progress | Chakrapani | 2nd Mar |  |  |  | failed
10 | Display the images in tumbnails |  | Chakrapani
11 | Multiple person uploading |  | Jadeja
| Publish development/production environment |  | shiva
12 | When the directory/date folder entered is not available, there is no pop up/error saying "no such directory exists" |  | Chakrapani |  |  |  |  | failed
13 | Delete the user data once the Athlete logs out |  | Jadeja |  |  |  |  | failed
14 | change the name to "Hound Dog by TeamFotog" |  | Chakrapani